## Dashboard
Queuing Solutions – Engineering Progress Dashboard
Overall Weighted % Complete:
Status | Count | % of Total
Fully Working
Partially Working
Scaffolded
Broken
Not Started
Module Group | % Complete (weighted) | Count
M0 – Platform Foundation
M1 – Company Onboarding
M10 – Super Admin Console
M11 – Frontend / Public Pages
M2 – Branch & Staff Management
M3 – Queue Method 1
M4 – Queue Method 2
M5 – Queue Method 3
M6 – Queue Method 4
M7 – KOT Kiosk
M8 – Notifications & Alerts
M9 – Analytics & Reporting
Priority | % Complete (weighted) | Count
Must
Should
Could
Top Blockers – Must-Priority Items (Worst Shape First)
ID | Feature | Status | Blocker
M11-04 | Password Reset / Forgot Password | Scaffolded | No backend reset endpoint; no token-based reset flow; email backend is console anyway
M1-04 | Stripe Checkout / Payment Integration | Partially Working | STRIPE_SECRET_KEY not in .env; StripeSimulatorView exists as sandbox fallback
M5-01 | Full-Screen Live Display Board (Now Serving) | Partially Working | display/views.py is empty (4 lines, no implementation). PublicDisplayView is in queuing/views.py but display app has no routes registered
M5-02 | Real-time Token Flip (WebSocket on display board) | Partially Working | Cannot confirm WS connection succeeds without runtime test
M8-03 | Automated Alert Checks (Celery periodic tasks) | Partially Working | Celery broker defaults to memory:// – tasks not durable; no Celery worker running in dev setup

## Module Audit
ID | Feature | Module Group | Priority | Status | % Complete | Backend Evidence | Frontend Evidence | End-to-End Wired? | Tested? | Confidence | Blockers | Next Step to Close Gap
M0-01 | Django Project Setup & ASGI Config | M0 – Platform Foundation | Must | Fully Working | 100 | backend/queuing_solutions/settings.py; asgi.py | N/A | Y | Y – test_phase1.py | High | None | —
M0-02 | MySQL/MariaDB Database & Migrations | M0 – Platform Foundation | Must | Fully Working | 100 | backend/queuing_solutions/settings.py; 9 migration dirs | N/A | Y | Y – test_models.py | High | MariaDB version-check monkey-patched (settings.py:17) | Upgrade XAMPP/MariaDB to ≥10.5 to remove monkey-patch
M0-03 | JWT Authentication (Login / Logout / Refresh) | M0 – Platform Foundation | Must | Fully Working | 100 | accounts/views.py – CustomTokenObtainPairView, LogoutView; /api/auth/login¦logout¦refresh | src/routes/login.tsx; src/lib/quesole/store.tsx:signIn() | Y | Y – test_auth.py (5 tests pass) | High | None | —
M0-04 | Role-Based Access Control (RBAC) | M0 – Platform Foundation | Must | Fully Working | 100 | core/permissions.py – IsSuperAdmin, IsCompanyAdmin, IsBranchAdmin, IsDeskStaff | src/routes/app.tsx – role-gated nav; src/lib/quesole/store.tsx | Y | Y – test_rbac.py (passes) | High | None | —
M0-05 | Multi-Tenant Isolation (company-scoped querysets) | M0 – Platform Foundation | Must | Fully Working | 100 | core/managers.py – TenantManager applied to all models | store.tsx filters by session.companyId | Y | Y – test_tenant_isolation.py (3 pass) | High | None | —
M0-06 | WebSocket / Django Channels (Real-time) | M0 – Platform Foundation | Must | Fully Working | 100 | core/consumers.py – QueueConsumer; queuing/views.py:broadcast_queue_update() | store.tsx:593 – ws://hostname:8000/ws/branch/… | Y | Y – test_websocket.py; test_phase2.py::test_websocket_pii_segregation | High | InMemoryChannelLayer used (no Redis configured) – not suitable for multi-process prod | Set REDIS_URL env var to switch to RedisChannelLayer
M0-07 | Health-check endpoint | M0 – Platform Foundation | Should | Fully Working | 100 | core/views.py:healthz; /healthz | N/A | Y | N | High | None | Add a smoke test
M0-08 | Audit Log (AuditLog model + write) | M0 – Platform Foundation | Should | Fully Working | 100 | audit/models.py; audit/utils.py:log_audit(); /api/audit-logs/ | super-admin.tsx renders audit log tab | Y | N – unit tests not found for audit | Medium | No dedicated audit tests | Add test_audit.py
M0-09 | API Schema / Swagger Docs | M0 – Platform Foundation | Could | Fully Working | 100 | drf_spectacular; /api/schema/ /api/docs/ /api/redoc/ | N/A | Y | N | High | None | —
M0-10 | Prometheus Metrics | M0 – Platform Foundation | Could | Fully Working | 100 | django_prometheus middleware; /metrics route | N/A | Y | N | Unverified | Not verified at runtime | Hit /metrics and confirm output
M1-01 | Company Registration (multi-step wizard) | M1 – Company Onboarding | Must | Fully Working | 100 | companies/views.py:CompanyRegistrationView; POST /api/companies/register/ | src/routes/signup.tsx (multi-step wizard, 42 KB) | Y | Y – test_phase1.py | High | CAPTCHA is MOCK_CAPTCHA_TOKEN on frontend ($companySlug.tsx:187) | Integrate real reCAPTCHA or hCaptcha
M1-02 | Subscription Package Selection (Starter/Standard/Advanced/Enterprise) | M1 – Company Onboarding | Must | Fully Working | 100 | billing/models.py:Package; /api/packages/ | src/routes/signup.tsx – plan selection step; src/routes/pricing.tsx | Y | Y – test_entitlements.py | High | None | —
M1-03 | Company Admin Account Creation on Signup | M1 – Company Onboarding | Must | Fully Working | 100 | companies/views.py:CompanyRegistrationView creates User(role=company_admin) | signup.tsx step 3 – Admin Credentials | Y | Y – test_phase1.py | High | None | —
M1-04 | Stripe Checkout / Payment Integration | M1 – Company Onboarding | Must | Partially Working | 50 | billing/views.py:CheckoutSessionView, StripeWebhookView; billing/stripe_helper.py | signup.tsx – payment step with card fields; /api/billing/checkout/ | N | N – no Stripe integration test | Unverified | STRIPE_SECRET_KEY not in .env; StripeSimulatorView exists as sandbox fallback | Add STRIPE_SECRET_KEY env var; test with Stripe test keys
M1-05 | Super Admin Company Approval Queue | M1 – Company Onboarding | Must | Fully Working | 100 | companies/views.py – CompanyViewSet with approve/reject actions; status field | super-admin.tsx – companies view with approve/reject buttons | Y | Y – test_company_admin.py | High | None | —
M1-06 | Upgrade Request Flow (company → super admin) | M1 – Company Onboarding | Should | Fully Working | 100 | billing/models.py:UpgradeRequest; /api/upgrades/ | super-admin.tsx upgrade_requests view; company-admin.tsx upgrade CTA | Y | N | Medium | None | Add upgrade request test
M1-07 | Invoice Generation & PDF Download | M1 – Company Onboarding | Should | Partially Working | 50 | billing/views.py:InvoiceViewSet, InvoiceDownloadView; /api/billing/invoices/{id}/download/ | company-admin.tsx – billing tab references invoices | N | Y – test_phase7.py covers invoice model | Unverified | PDF generation library (weasyprint/reportlab?) not verified in requirements.txt | Check billing/views.py InvoiceDownloadView implementation; confirm PDF lib installed
M1-08 | Add-On Purchase (buy more desks/branches) | M1 – Company Onboarding | Should | Partially Working | 50 | billing/views.py:BuyAddOnView, CheckoutUpgradeView; /api/billing/buy-addon/ | billing-plan-configurator.tsx (108 KB component) | N | N | Unverified | Depends on Stripe; no integration test | Wire Stripe test keys and run manual flow
M1-09 | Itemised Plan Configurator (branch/desk/kiosk pricing) | M1 – Company Onboarding | Could | Fully Working | 100 | billing/models.py:PlanComponent,CompanyPlanAllocation; /api/billing/plan-components/ /api/billing/allocations/ | src/components/console/billing-plan-configurator.tsx | Y | Y – test_phase7.py | High | None | —
M2-01 | Branch CRUD (create/edit/archive) | M2 – Branch & Staff Management | Must | Fully Working | 100 | branches/views.py:BranchViewSet; /api/branches/ | company-admin.tsx – branch management tab | Y | Y – test_phase1.py | High | None | —
M2-02 | Branch Seat / Plan Limit Enforcement | M2 – Branch & Staff Management | Must | Fully Working | 100 | branches/views.py:BranchViewSet.perform_create() checks max_branches; billing/models.py | company-admin.tsx shows limit warnings | Y | Y – test_entitlements.py | High | None | —
M2-03 | Staff User Invite System | M2 – Branch & Staff Management | Must | Fully Working | 100 | accounts/views.py:UserInviteViewSet; /api/invites/; InviteAcceptView | company-admin.tsx – staff tab with invite modal | Y | Y – test_company_admin.py | High | Email invite delivery uses console backend (no SMTP configured) | Configure SMTP or email provider in .env
M2-04 | Role Assignment (company_admin / branch_admin / desk_staff) | M2 – Branch & Staff Management | Must | Fully Working | 100 | accounts/models.py:User.role field; serializers enforce choices | invite modal + staff edit; role-switcher in shell | Y | Y – test_rbac.py | High | None | —
M2-05 | User Seat Limit Enforcement (max_users) | M2 – Branch & Staff Management | Must | Fully Working | 100 | accounts/views.py:UserInviteViewSet.perform_create() checks seat limit | Shows error toast when limit hit | Y | Y – test_entitlements.py | High | None | —
M2-06 | Desk CRUD + Service Assignment | M2 – Branch & Staff Management | Must | Fully Working | 100 | queuing/views.py:DeskViewSet,ServiceViewSet,DeskServiceViewSet; /api/desks/ /api/services/ | src/components/console/branch-desks-services.tsx (156 KB) | Y | Y – test_phase2.py | High | None | —
M2-07 | Staff-to-Desk & Staff-to-Service Assignment | M2 – Branch & Staff Management | Must | Fully Working | 100 | queuing/views.py:UserServiceViewSet,DeskStaffAssignmentViewSet; /api/user-services/ /api/desk-staff-assignments/ | branch-desks-services.tsx – staff assignment UI | Y | Y – test_phase2.py | High | None | —
M2-08 | Branch Timezone Configuration | M2 – Branch & Staff Management | Should | Fully Working | 100 | branches/models.py:Branch.timezone field | branch-console.tsx – settings tab | Y | N | Medium | None | Add timezone-aware scheduling test
M3-01 | QR Code Generation per Branch/Method | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/views.py:QrCodeGenerateView; /api/branches/{id}/generate-qr/; qrcodes/ dir has SVG files | branch-desks-services.tsx – QR code preview & download | Y | Y – test_phase2.py | High | None | —
M3-02 | Public QR Landing Page (customer joins queue) | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/views.py:PublicJoinQueueView; POST /api/public/join/ | src/routes/q.$branchId.tsx (18 KB) | Y | Y – test_phase2.py::test_public_join_queue | High | None | —
M3-03 | Token Number Generation (sequential, prefix) | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/models.py:TokenSequence.get_next_sequence_number(); atomic select_for_update | Token displayed after join | Y | Y – test_phase2.py | High | None | —
M3-04 | Operator 'Call Next' Console | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/views.py:TicketViewSet call_next action; POST /api/tickets/call-next/ | src/routes/app.tsx – desk console tab; branch-console.tsx | Y | Y – test_phase2.py | High | None | —
M3-05 | Ticket Actions (Serve / No-Show / Skip / Transfer / Hold / Cancel) | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/views.py:TicketViewSet action(); POST /api/tickets/{id}/action/ | branch-console.tsx – ticket action buttons | Y | Y – test_phase2.py | High | None | —
M3-06 | Live Queue Tracking Page (customer) | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/views.py:PublicTicketDetailView; /api/public/ticket/{id}/ | src/routes/t.$ticketId.tsx (7 KB) – position + ETA | Y | N – no public tracking test | Medium | None | Add test for public tracking endpoint
M3-07 | Geolocation Verification at Join | M3 – Queue Method 1 | Should | Fully Working | 100 | queuing/views.py:VerifyLocationView; POST /api/public/verify-location/ | q.$branchId.tsx – location permission prompt | Y | N | Medium | None | Add location verification test
M3-08 | Ticket Note by Operator | M3 – Queue Method 1 | Should | Fully Working | 100 | queuing/models.py:TicketNote; queuing/views.py:TicketNoteSerializer | branch-console.tsx – note input | Y | Y – test_phase2.py | High | None | —
M3-09 | PII Encryption (customer phone) | M3 – Queue Method 1 | Must | Fully Working | 100 | queuing/models.py:Ticket.customer_phone = EncryptedCharField; blind index for search | N/A (backend concern) | Y | Y – test_phase2.py::test_websocket_pii_segregation | High | FIELD_ENCRYPTION_KEY uses insecure default if not set in .env | Set strong FIELD_ENCRYPTION_KEY in .env
M4-01 | Service-Based Queue Routing (auto-assign desk) | M4 – Queue Method 2 | Must | Fully Working | 100 | queuing/services/queue_routing.py – assign_predicted_desk_for_ticket(); Ticket.save() calls it | q.$branchId.tsx – service selector | Y | Y – test_phase2.py | High | None | —
M4-02 | Desk Deactivation → Ticket Redistribution | M4 – Queue Method 2 | Must | Fully Working | 100 | queuing/models.py:Desk.save() calls redistribute_tickets_for_deactivated_desk() | N/A | Y | N | Medium | None | Add desk deactivation redistribution test
M4-03 | Manual Ticket Issuance (counter staff) | M4 – Queue Method 2 | Should | Fully Working | 100 | queuing/views.py:ManualTicketIssueView; POST /api/tickets/manual-issue/ | branch-console.tsx – manual issue button | Y | N | Medium | None | Add manual issue test
M5-01 | Full-Screen Live Display Board (Now Serving) | M5 – Queue Method 3 | Must | Partially Working | 50 | queuing/views.py:PublicDisplayView; /api/public/display/{branchId}/ | src/routes/display.$branchId.tsx (23 KB) – NOW SERVING flip animation | N | N | Unverified | display/views.py is empty (4 lines, no implementation). PublicDisplayView is in queuing/views.py but display app has no routes registered | Wire display app URLs to main router; verify PublicDisplayView returns correct data
M5-02 | Real-time Token Flip (WebSocket on display board) | M5 – Queue Method 3 | Must | Partially Working | 50 | core/consumers.py:QueueConsumer broadcasts to branch_{id}_public group | display.$branchId.tsx:325 opens ws://hostname:8000/ws/branch/{id}/public/ | N | N | Unverified | Cannot confirm WS connection succeeds without runtime test | Run display board in browser and verify WS connection
M6-01 | Public Appointment Booking Portal | M6 – Queue Method 4 | Must | Fully Working | 100 | appointments/views.py:AppointmentBookingView; POST /api/public/appointments/book/ | src/routes/$companySlug.tsx (30 KB); src/routes/book.tsx (12 KB) | Y | Y – test_phase4.py | High | CAPTCHA is MOCK_CAPTCHA_TOKEN | Integrate real CAPTCHA
M6-02 | OTP Verification (send / verify) | M6 – Queue Method 4 | Must | Fully Working | 100 | appointments/views.py:OtpSendView, OtpVerifyView; /api/public/appointments/otp/send¦verify/ | $companySlug.tsx – OTP step; src/components/quesole/otp.tsx | Y | Y – test_phase4.py | High | SMS OTP uses console backend by default (SMS_BACKEND=console) | Configure MSG91_AUTH_KEY or TWILIO credentials for real SMS delivery
M6-03 | Appointment Slot Management (create/bulk/list) | M6 – Queue Method 4 | Must | Fully Working | 100 | appointments/views.py:AppointmentSlotViewSet, BulkSlotCreateView, TimeSlotViewSet | branch-console.tsx – appointment tab | Y | Y – test_phase4.py | High | None | —
M6-04 | Appointment Reschedule & Cancel (manage link) | M6 – Queue Method 4 | Must | Fully Working | 100 | appointments/views.py:AppointmentManageView, AppointmentRescheduleView, AppointmentCancelView | $companySlug.tsx – manage section | Y | Y – test_phase4.py | High | None | —
M6-05 | Online Booking Portal (company slug URL) | M6 – Queue Method 4 | Must | Fully Working | 100 | appointments/views.py:PublicCompanyResolveView; /api/public/company/{slug}/ | src/routes/$companySlug.tsx – full booking flow | Y | N | Medium | None | Add e2e booking flow test
M6-06 | Booking Page Config (admin configures booking page) | M6 – Queue Method 4 | Should | Fully Working | 100 | appointments/views.py:BookingPageConfigView; /api/public/company-booking-config/ | branch-console.tsx – booking config tab | Y | N | Medium | None | —
M7-01 | Kiosk Touch Interface (service select + token) | M7 – KOT Kiosk | Must | Fully Working | 100 | kot/views.py:KioskJoinView; POST /api/kiosk/join/ (via kot.urls) | src/routes/kiosk.$branchId.tsx (52 KB – largest route file) | Y | Y – test_phase3.py | High | None | —
M7-02 | KOT Printer Management (register / heartbeat) | M7 – KOT Kiosk | Must | Fully Working | 100 | kot/views.py:PrinterViewSet, PrinterHeartbeatView, PrinterJobsView, PrinterJobCompleteView | branch-desks-services.tsx – printer config tab | Y | Y – test_phase3.py | High | Printer authentication uses 'PrinterToken' scheme – not standard JWT | Document printer token scheme; add printer integration test
M7-03 | KOT Print Job Queue | M7 – KOT Kiosk | Must | Fully Working | 100 | kot/models.py:KotPrintJob; kot/views.py:PrinterJobsView, PrinterJobCompleteView | N/A (consumed by printer device) | Y | Y – test_phase3.py | High | None | —
M7-04 | Kiosk Staff Override PIN | M7 – KOT Kiosk | Should | Scaffolded | 25 | N/A – no backend PIN endpoint found | kiosk.$branchId.tsx:679 – PIN input UI exists | N | N | Medium | No backend endpoint to validate PIN; UI collects PIN but doesn't submit it to an API | Implement POST /api/kiosk/staff-override/ with PIN verification
M8-01 | In-App Notification Center | M8 – Notifications & Alerts | Must | Fully Working | 100 | notifications/models.py:Notification; /api/notifications/ | shell.tsx – notification bell + unread badge | Y | N – notifications/tests.py is empty (60 bytes) | Medium | No notification tests | Write test_notifications.py
M8-02 | Alert Rule Builder (company admin) | M8 – Notifications & Alerts | Must | Fully Working | 100 | notifications/views.py:AlertRuleViewSet; /api/alert-rules/ | company-admin.tsx – alert rules tab | Y | N | Medium | None | Add alert rule CRUD tests
M8-03 | Automated Alert Checks (Celery periodic tasks) | M8 – Notifications & Alerts | Must | Partially Working | 50 | notifications/tasks.py (23 KB) – 8 periodic tasks (long_wait, queue_spike, desk_idle, no_show, device_heartbeat, no_operator, SLA, volume_anomaly) | N/A | N | N | Unverified | Celery broker defaults to memory:// – tasks not durable; no Celery worker running in dev setup | Start Celery worker; configure Redis broker; add task tests
M8-04 | SMS / Email Notifications | M8 – Notifications & Alerts | Should | Scaffolded | 25 | notifications/tasks.py:dispatch_notification() routes to console/SMS; accounts/services/ dir exists | N/A | N | N | Unverified | SMS_BACKEND=console; no TWILIO/MSG91 credentials configured; email backend is console | Configure SMS/email provider credentials in .env
M8-05 | Notification Templates | M8 – Notifications & Alerts | Should | Fully Working | 100 | notifications/views.py:NotificationTemplateViewSet; /api/notification-templates/; billing/templates/ dir | N/A | Y | N | Medium | None | —
M9-01 | Report Trends API | M9 – Analytics & Reporting | Must | Fully Working | 100 | analytics/views.py:ReportTrendsView; GET /api/reports/trends/ | company-admin.tsx – analytics tab with charts | Y | Y – test_phase5.py | High | None | —
M9-02 | CSV/Excel Export | M9 – Analytics & Reporting | Must | Fully Working | 100 | analytics/views.py:ReportExportView; GET /api/reports/export/ (uses pandas) | company-admin.tsx – export button | Y | Y – test_phase5.py | High | None | —
M9-03 | Peak-Hour Heatmap | M9 – Analytics & Reporting | Should | Fully Working | 100 | analytics/views.py:ReportTrendsView returns peak_hours dict | company-admin.tsx renders heatmap chart | Y | N | Medium | None | —
M9-04 | Staff Performance Report | M9 – Analytics & Reporting | Should | Fully Working | 100 | analytics/views.py returns staff_summary from ReportSnapshot.metrics | company-admin.tsx – staff performance panel | Y | N | Medium | Report data depends on ReportSnapshot being populated (analytics/tasks.py) | Verify ReportSnapshot gets populated by Celery task
M9-05 | Branch Comparison Report | M9 – Analytics & Reporting | Could | Fully Working | 100 | analytics/views.py:branch_comp dict in ReportTrendsView | company-admin.tsx – branch comparison tab | Y | N | Medium | None | —
M10-01 | Platform KPI Dashboard | M10 – Super Admin Console | Must | Fully Working | 100 | /api/companies/, /api/branches/, etc – data aggregated on frontend | super-admin.tsx – dashboard view with MRR, waiting count, upgrades | Y | N | Medium | MRR calculated from company.monthlySpend (local state field, not a backend aggregate) | Add dedicated platform KPI API endpoint
M10-02 | Package/Plan Editor (CRUD) | M10 – Super Admin Console | Must | Fully Working | 100 | billing/views.py:PlanComponentViewSet (IsSuperAdmin gated); /api/billing/plan-components/ | super-admin.tsx – billing/plan components tab | Y | N | Medium | None | —
M10-03 | Platform Audit Log Viewer | M10 – Super Admin Console | Should | Fully Working | 100 | audit/views.py:AuditLogViewSet; /api/audit-logs/ | super-admin.tsx – audit log tab | Y | N | Medium | None | —
M10-04 | Platform Settings (global config) | M10 – Super Admin Console | Should | Partially Working | 50 | core/models.py:PlatformSetting model; companies/views.py reads it | super-admin.tsx – settings tab renders some config | N | N | Unverified | No dedicated /api/platform-settings/ endpoint found in urls.py | Register PlatformSetting CRUD endpoint
M10-05 | Price Change Log | M10 – Super Admin Console | Could | Fully Working | 100 | billing/models.py:PriceChangeLog; /api/billing/price-change-logs/ | super-admin.tsx – plan pricing tab | Y | N | Medium | None | —
M11-01 | Marketing Landing Page | M11 – Frontend / Public Pages | Must | Fully Working | 100 | N/A | src/routes/index.tsx; src/components/site/sections.tsx (multiple sections) | Y | N | High | None | —
M11-02 | Pricing Page | M11 – Frontend / Public Pages | Must | Fully Working | 100 | /api/billing/plan-components/ – pricing data from API | src/routes/pricing.tsx (16 KB) | Y | N | High | None | —
M11-03 | Login Page | M11 – Frontend / Public Pages | Must | Fully Working | 100 | /api/auth/login/ (JWT) | src/routes/login.tsx (18 KB) | Y | Y – test_auth.py | High | None | —
M11-04 | Password Reset / Forgot Password | M11 – Frontend / Public Pages | Must | Scaffolded | 25 | N/A – no reset endpoint in urls.py | src/routes/forgot-password.tsx (7 KB) – UI exists | N | N | High | No backend reset endpoint; no token-based reset flow; email backend is console anyway | Implement POST /api/auth/password-reset/ + confirm endpoint
M11-05 | App Shell & Role-Based Navigation | M11 – Frontend / Public Pages | Must | Fully Working | 100 | N/A | src/routes/app.tsx; src/components/console/shell.tsx – sidebar, role nav | Y | N | High | None | —
M11-06 | Company Admin Console | M11 – Frontend / Public Pages | Must | Fully Working | 100 | Multiple API endpoints wired | src/components/console/company-admin.tsx (120 KB) | Y | Y – test_company_admin.py | High | None | —
M11-07 | Branch Admin Console | M11 – Frontend / Public Pages | Must | Fully Working | 100 | Multiple API endpoints wired | src/components/console/branch-console.tsx (61 KB); branch-desks-services.tsx | Y | N | High | None | —
M11-08 | Operator / Desk Console | M11 – Frontend / Public Pages | Must | Fully Working | 100 | /api/tickets/call-next/; /api/tickets/{id}/action/ | app.tsx – desk console tab; branch-console.tsx | Y | Y – test_phase2.py | High | None | —
M11-09 | Customer Feedback (post-service rating) | M11 – Frontend / Public Pages | Should | Scaffolded | 25 | feedback/models.py:Feedback (model only); no views.py; no URL registered | N/A – no feedback UI found in routes/components | N | N | High | Model exists, zero API surface and no frontend | Implement feedback views.py, urls.py, and customer-facing feedback page
M11-10 | Data Backup & Retention (PII purge + DB backup) | M11 – Frontend / Public Pages | Could | Partially Working | 50 | core/backup.py:run_mysql_backup(); core/tasks.py:purge_expired_customer_pii(); Celery beat schedules both | N/A | N | Y – test_phase7.py covers PII purge logic | Unverified | Celery must be running; DB backup uses mysqldump which must be on PATH | Run Celery beat; verify mysqldump available; test backup file creation

## Untracked - Extra Code
Path / Location | Description
src/components/site/scroll-controlled-background.tsx | Scroll-linked background video (MOD-01 from completed_modules.xlsx) – frontend-only visual enhancement, not in main spec
completed_modules.xlsx | Separate UI polish module tracker (MOD-01…MOD-10) tracking frontend visual improvements – not in main breakdown sheet
backend/tests/locustfile.py | Locust load-testing script (~200 lines) – not listed in spec but useful
backend/tests/test_scenario57.py | Specific scenario test file named 'scenario57' – purpose unclear from name alone
backend/billing/stripe_helper.py | Stripe helper module (3 KB) wrapping stripe API – not explicitly in breakdown as separate module
backend/core/honeypot.py | Bot honeypot field validator – security extra beyond spec
backend/core/throttles.py | Custom DRF throttle classes – beyond baseline spec
backend/core/crypto.py | Custom blind-index + tracking-code generator – beyond spec, supports PII encryption
backend/subscriptions/ | Empty subscriptions/ app directory – stubs with only a services/ subdir; functionality is in billing/ instead
backend/qrcodes/ | qrcodes/ directory contains only SVG files (static assets) – not an app module
backend/backups/ | backups/ directory – runtime backup output location (not a Django app)
src/routes/book.tsx | Standalone book.tsx route (12 KB) – partial overlap with $companySlug.tsx booking flow; may be unused or alternate flow
backend/tests/test_phase6.py | Phase 6 tests (6 KB) – covers functionality not in M0-M11 breakdown (possibly security/compliance phase)
backend/tests/test_phase7.py | Phase 7 tests (36 KB, largest test file) – covers data retention, backup, compliance beyond main spec
src/lib/quesole/store.tsx:1601 | store.tsx line 1601 comment: 'Calculated mock/live trend percentages vs. yesterday/last hour' – dashboard delta percentages are computed locally, not from backend