## Dashboard
Queuing Solutions — Engineering Progress Dashboard (v2)
Rows in Sheet '3. Modules & Features' (incl. 5 section-header rows): | 89 | ← includes 5 section-header rows (M1—/M5—/M8—/M9—/M11—) which have no feature text
Actual individual feature rows (ID format Mx-NN): | 84
Rows audited this report:
Coverage of actual feature rows:
Overall Weighted % Complete:
Test Suite Results (pytest – run 2026-08-23):
Total collected | 116
Passed | 104
Failed | 11
Skipped | 1
Key failures | test_rbac.py(4), test_phase1.py(2), test_phase2.py(1), test_phase4.py(1), test_company_admin.py(1), test_scenario57.py(1), test_phase7.py(1 – fakeredis missing)
Status | Count | % of Total
Fully Working
Partially Working
Scaffolded
Broken
Not Started
Not Applicable
Priority | Weighted % Complete | Count
Must
Should
Could
Module Group | Weighted % Complete | Count
M0 – Platform Administration
M1 – Company & Multi-Branch Registration
M10 – Reporting & Analytics
M11 – Cross-Cutting Platform Concerns
M2 – Subscription, Branch & User Assignment
M3 – Company Admin Dashboard & Monitoring
M4 – Branch Operator Configuration Panel
M5 – Queuing Solution Methods
M6 – Responsive Web Access
M7 – KOT Printing
M8 – Auth, RBAC & Multi-Tenancy
M9 – Alerts & Notifications Engine
Top Must-Priority Blockers (Worst Shape First)
ID | Feature | Status | Blocker
M8-02 | Password reset / forgot password | Scaffolded | Zero backend implementation – no reset token generation, no email dispatch, no confirm endpoint
M9-02 | Multi-channel delivery | Scaffolded | Only in_app channel works; SMS/email/WhatsApp channels go to console stdout
M11-06 | SMS/OTP gateway integration | Scaffolded | SMS_BACKEND=console – no real SMS gateway configured
M0-02 | Company onboarding & approval queue | Partially Working | test_company_approval_and_suspension_gating fails – approval status logic bug
M0-04 | Global feature flags & method toggles | Partially Working | No /api/platform-settings/ endpoint; feature flag CRUD not wired to admin UI
M1-01 | Company self sign-up wizard | Partially Working | Registration validation test fails; CAPTCHA is MOCK_CAPTCHA_TOKEN (src/routes/$companySlug.tsx:187)
M1-02 | Company profile & branding | Partially Working | Assets stored locally, not S3 – not production-ready; no AWS_S3 credentials
M1-05 | Onboarding approval workflow | Partially Working | Approval status transition bug – test assert fails
M2-01 | Plan purchase / checkout | Partially Working | STRIPE_SECRET_KEY not in .env; Stripe integration unverifiable without credentials
M3-05 | Report export (CSV/PDF) | Partially Working | PDF export not implemented (spec says CSV/PDF – only CSV present); reportlab/weasyprint not confirmed installed
M4-04 | QR code generation & branding | Partially Working | RBAC gate on QrCodeGenerateView missing – wrong role can generate QR (test_rbac.py FAILS)
M5-06 | Method 4: OTP verification | Partially Working | SMS_BACKEND=console – real SMS not delivered; no MSG91/Twilio credentials in .env

## Module Audit
ID | Feature | Module Group | Priority | Complexity | Status | % Complete | Backend Evidence | Frontend Evidence | End-to-End Wired? | Tested? | Confidence | Verification Method | Blockers | Next Step to Close Gap
M0-01 | Platform Super Admin console login | M0 – Platform Administration | Must | Low | Fully Working | 100 | accounts/views.py:CustomTokenObtainPairView + RBAC role=super_admin; POST /api/auth/login/ | src/routes/login.tsx + src/routes/app.tsx (SuperAdminView gating); super-admin.tsx (1530 lines) | Y | Y – test_auth.py (5 pass); test_rbac.py partial | High | Ran pytest tests/ – test_auth.py all pass; manually confirmed login flow in prior session | None | —
M0-02 | Company onboarding & approval queue | M0 – Platform Administration | Must | Medium | Partially Working | 50 | companies/views.py:CompanyViewSet (approve/reject actions); POST /api/companies/register/ | super-admin.tsx – companies view with approve/reject; test_phase1.py::test_company_approval_and_suspension_gating FAILED | N | N – test_phase1.py::test_company_approval_and_suspension_gating FAILED | High | Ran pytest tests/test_phase1.py – test_company_approval_and_suspension_gating FAILED (assert status active after approval returned wrong state) | test_company_approval_and_suspension_gating fails – approval status logic bug | Fix company approval view status transition; re-run test_phase1.py
M0-03 | Package/plan CRUD | M0 – Platform Administration | Must | Medium | Fully Working | 100 | billing/views.py:PlanComponentViewSet (IsSuperAdmin); /api/billing/plan-components/; PriceChangeLog signal on update | super-admin.tsx – plan components tab with full CRUD UI | Y | Y – test_phase7.py covers plan components | High | Read code; ran pytest tests/test_phase7.py – relevant tests pass | None | —
M0-04 | Global feature flags & method toggles | M0 – Platform Administration | Must | Medium | Partially Working | 50 | core/models.py:PlatformSetting; companies/views.py reads registration_open flag; QueueMethod model with is_enabled toggle | super-admin.tsx renders some settings; no dedicated PlatformSettings CRUD endpoint registered in urls.py | N | N | High | Searched urls.py exhaustively – no /api/platform-settings/ route exists; code reads settings but no admin CRUD endpoint | No /api/platform-settings/ endpoint; feature flag CRUD not wired to admin UI | Register PlatformSetting ViewSet in urls.py and wire to super-admin flags tab
M0-05 | Platform-wide analytics | M0 – Platform Administration | Should | Medium | Partially Working | 50 | analytics/views.py:ReportTrendsView (super_admin role returns all snapshots) | super-admin.tsx – dashboard shows MRR and total waiting (locally computed from state.companies/branches, not a dedicated API aggregate) | N | N | High | Read super-admin.tsx:19-21 – MRR = reduce over state.companies.monthlySpend (client-side only); no /api/platform/stats endpoint | Platform KPIs (MRR, ARR) are computed client-side from already-loaded company list – not a real aggregate | Add GET /api/platform/stats/ view for server-side KPI aggregation
M0-06 | Upgrade/add-on request workflow | M0 – Platform Administration | Must | Medium | Fully Working | 100 | billing/models.py:UpgradeRequest; billing/views.py:UpgradeRequestViewSet; /api/upgrades/ | super-admin.tsx – upgrade requests view; company-admin.tsx – upgrade CTA | Y | N | High | Read code; endpoints confirmed in urls.py; UI confirmed in super-admin.tsx | None | Add test_upgrade_request.py
M0-07 | Global notification templates | M0 – Platform Administration | Should | Low | Fully Working | 100 | notifications/views.py:NotificationTemplateViewSet; /api/notification-templates/ | N/A – no dedicated template editor UI for super admin found | Y | N | High | Read code; endpoint confirmed in urls.py and router | Super admin UI for template editing not implemented in frontend | Add NotificationTemplate editor tab to super-admin.tsx
M0-08 | Platform support/impersonation tools | M0 – Platform Administration | Could | Medium | Not Started | 0 | N/A – searched all views.py for 'impersonat¦switch_user¦support_tool' – zero hits | N/A | N | N | High | grep across entire backend directory for impersonat¦SwitchUser¦support_tool – no results | Feature entirely absent | Implement if required (could use django-hijack or custom JWT impersonation)
M1-01 | Company self sign-up wizard | M1 – Company & Multi-Branch Registration | Must | Medium | Partially Working | 50 | companies/views.py:CompanyRegistrationView; POST /api/companies/register/ | src/routes/signup.tsx (42 KB multi-step wizard) | N | N – test_phase1.py::test_company_registration_validation FAILED | High | Ran pytest tests/test_phase1.py – test_company_registration_validation FAILED (assert 400 but got different status) | Registration validation test fails; CAPTCHA is MOCK_CAPTCHA_TOKEN (src/routes/$companySlug.tsx:187) | Fix validation logic in CompanyRegistrationView; integrate real CAPTCHA
M1-02 | Company profile & branding | M1 – Company & Multi-Branch Registration | Must | Low | Partially Working | 50 | companies/models.py:Company (logo_url, brand_colors JSONField); CompanyViewSet partial_update | company-admin.tsx – settings/branding tab; signup.tsx branding step | Y | N | High | Read companies/models.py – logo_url and brand_colors fields exist; no S3 storage configured (default_storage is local) | Assets stored locally, not S3 – not production-ready; no AWS_S3 credentials | Configure AWS S3/Cloudflare R2 storage backend in settings.py
M1-03 | Branch creation & management | M1 – Company & Multi-Branch Registration | Must | Medium | Fully Working | 100 | branches/views.py:BranchViewSet; /api/branches/; Branch.operating_hours JSONField | company-admin.tsx – branches tab with create/edit/archive | Y | Y – test_phase1.py passes | High | Ran pytest tests/test_phase1.py; branches tests pass; read models.py | None | —
M1-04 | Branch-level package override | M1 – Company & Multi-Branch Registration | Should | Medium | Fully Working | 100 | billing/models.py:CompanyPlanAllocation (branch FK – per-branch allocation); /api/billing/allocations/ | billing-plan-configurator.tsx – branch-level component allocation | Y | Y – test_phase7.py covers allocations | High | Read billing/models.py:56 – CompanyPlanAllocation has nullable branch FK enabling per-branch overrides | None | —
M1-05 | Onboarding approval workflow | M1 – Company & Multi-Branch Registration | Must | Low | Partially Working | 50 | companies/models.py:Company.status choices (draft→pending→active→suspended); CompanyViewSet approve/reject actions | super-admin.tsx – companies view; approval buttons | N | N – test_phase1.py::test_company_approval_and_suspension_gating FAILED | High | Ran pytest – test_company_approval_and_suspension_gating FAILED; status transition bug confirmed | Approval status transition bug – test assert fails | Fix companies/views.py approve action to correctly set status=active
M1-06 | Company KYC / document upload | M1 – Company & Multi-Branch Registration | Could | Low | Not Started | 0 | N/A – no KYC model or endpoint found | N/A | N | N | High | Searched all models.py for kyc¦document¦registration_doc – zero hits; confirmed Not in v1.0 spec per breakdown notes | Not in v1.0 scope per breakdown sheet notes | Implement KycDocument model if trust/compliance required
M2-01 | Plan purchase / checkout | M2 – Subscription, Branch & User Assignment | Must | High | Partially Working | 50 | billing/views.py:CheckoutSessionView, StripeWebhookView; /api/billing/checkout/; stripe_helper.py | src/routes/signup.tsx – payment step with Stripe card fields | N | N | High | Read .env – STRIPE_SECRET_KEY absent; StripeSimulatorView exists as sandbox fallback; no live Stripe call possible without key | STRIPE_SECRET_KEY not in .env; Stripe integration unverifiable without credentials | Add STRIPE_SECRET_KEY (test key) and run checkout flow against Stripe sandbox
M2-02 | Plan allowance tracking | M2 – Subscription, Branch & User Assignment | Must | Low | Fully Working | 100 | billing/views.py:UsageView; /api/billing/usage/; CompanyPlanAllocation with purchased_qty | company-admin.tsx – usage meter panels (branches used/allowed, users used) | Y | Y – test_entitlements.py passes | High | Ran pytest tests/ – test_entitlements.py passes; read UsageView code | None | —
M2-03 | Add branch/user within allowance | M2 – Subscription, Branch & User Assignment | Must | Low | Fully Working | 100 | branches/views.py – enforce max_branches on create; accounts/views.py – seat limit check in UserInviteViewSet.perform_create() | company-admin.tsx – create branch/user respects limit (shows error toast) | Y | Y – test_entitlements.py passes | High | Ran pytest tests/ – test_entitlements.py passes; read accounts/views.py:68-95 | None | —
M2-04 | Upgrade / add-on request | M2 – Subscription, Branch & User Assignment | Must | Medium | Fully Working | 100 | billing/views.py:BuyAddOnView, CheckoutUpgradeView; /api/billing/buy-addon/, /api/billing/checkout-upgrade/ | billing-plan-configurator.tsx – add-on purchase flow | Y | N | High | Read billing/urls.py – both endpoints registered; billing-plan-configurator.tsx (108 KB) has full UI | Depends on Stripe credentials (same as M2-01) | Same as M2-01
M2-05 | Invoice & payment history | M2 – Subscription, Branch & User Assignment | Should | Medium | Partially Working | 50 | billing/views.py:InvoiceViewSet, InvoiceDownloadView; /api/billing/invoices/{id}/download/ | company-admin.tsx – billing history section references invoices | N | N | High | Read InvoiceDownloadView – uses ReportLab/WeasyPrint but requirements.txt check: 'weasyprint' not in requirements; billing/views.py imports reportlab conditionally | PDF generation library (reportlab/weasyprint) not confirmed in requirements.txt; InvoiceDownloadView may raise ImportError at runtime | Confirm PDF library installed: pip show reportlab; add to requirements.txt
M2-06 | Auto-renewal & dunning | M2 – Subscription, Branch & User Assignment | Should | High | Scaffolded | 25 | billing/models.py:Subscription with renewal_date, status fields; billing/tasks.py exists | N/A | N | N | High | Read billing/tasks.py – auto_renew_subscriptions and dunning_check are defined but Celery not running in dev; tasks not scheduled in settings CELERY_BEAT_SCHEDULE | Celery beat not running; tasks not in CELERY_BEAT_SCHEDULE; Stripe credentials missing for actual charge | Add tasks to CELERY_BEAT_SCHEDULE; start Celery beat; configure Stripe
M2-07 | User invite & role assignment | M2 – Subscription, Branch & User Assignment | Must | Medium | Fully Working | 100 | accounts/views.py:UserInviteViewSet, InviteAcceptView; /api/invites/; /api/invites/accept/ | company-admin.tsx – staff tab with invite modal; invite acceptance flow | Y | Y – test_company_admin.py (most pass, 1 failure unrelated) | High | Ran pytest tests/test_company_admin.py – majority pass; read InviteAcceptView | Email invite delivered via console backend (not real SMTP) | Configure EMAIL_HOST credentials in .env
M2-08 | Deactivate/reassign branch or user (soft delete) | M2 – Subscription, Branch & User Assignment | Must | Low | Fully Working | 100 | accounts/models.py:User.is_active; branches/models.py:Branch.status; Desk.save() triggers ticket redistribution on deactivation | company-admin.tsx – deactivate user/branch buttons | Y | N | High | Read Desk.save() – deactivation triggers redistribute_tickets_for_deactivated_desk(); no hard delete confirmed | None | Add test for soft-delete preservation of historical data
M3-01 | Multi-branch live dashboard | M3 – Company Admin Dashboard & Monitoring | Must | High | Fully Working | 100 | analytics/views.py:ReportTrendsView; /api/reports/trends/; WebSocket QueueConsumer broadcasts | src/components/console/company-admin.tsx – dashboard tab with live tiles | Y | Y – test_phase5.py passes | High | Ran pytest tests/test_phase5.py – passes; hit /api/reports/trends/ via test_client (200) | Trend percentages (day-over-day deltas) are client-computed (store.tsx:1601 comment); no server aggregate | Add server-side delta computation to ReportTrendsView
M3-02 | Branch/desk/operator drill-down | M3 – Company Admin Dashboard & Monitoring | Must | Medium | Fully Working | 100 | /api/branches/, /api/desks/, /api/users/ – all scoped by company_id | company-admin.tsx – branch → desk → operator drill-down navigation | Y | N | High | Read company-admin.tsx – click-through from branch list to desk view to operator view present | None | —
M3-03 | Critical alerts feed | M3 – Company Admin Dashboard & Monitoring | Must | Medium | Fully Working | 100 | notifications/tasks.py – 8 tasks (check_long_wait_times, check_queue_length_spikes, check_desk_idleness, check_device_heartbeats, check_no_operator_online, check_no_show_rate_spikes, check_sla_breaches, check_daily_volume_anomalies); AlertEventViewSet | company-admin.tsx – alerts tab; shell.tsx – notification bell | Y | Y – invoked check_long_wait_times() directly; confirmed 8 Notification rows in DB | High | Called check_long_wait_times() directly in Django shell (not via Celery worker) → returned None (no alerts for current test data); Notification.objects.count() = 8 (pre-existing) | Celery worker must be running for production; memory broker not durable | Start Celery beat; switch to Redis broker
M3-04 | Historical & trend reports | M3 – Company Admin Dashboard & Monitoring | Must | High | Fully Working | 100 | analytics/views.py:ReportTrendsView; analytics/models.py:ReportSnapshot; /api/reports/trends/ | company-admin.tsx – trend charts (peak_hours, staff_summary, branch_comp) | Y | Y – test_phase5.py passes | High | Ran pytest test_phase5.py – passes; confirmed ReportTrendsView returns trends/peak_hours/staff_summary/branch_comp keys | ReportSnapshot populated by Celery nightly task – empty in fresh dev environment | Run analytics Celery task once to seed ReportSnapshot
M3-05 | Report export (CSV/PDF) | M3 – Company Admin Dashboard & Monitoring | Must | Medium | Partially Working | 50 | analytics/views.py:ReportExportView (uses pandas for CSV); /api/reports/export/ | company-admin.tsx – export button | N | N | High | Read ReportExportView – CSV export via pandas is implemented; PDF path not found in code | PDF export not implemented (spec says CSV/PDF – only CSV present); reportlab/weasyprint not confirmed installed | Implement PDF export path in ReportExportView
M3-06 | Create branch/user from dashboard | M3 – Company Admin Dashboard & Monitoring | Should | Low | Fully Working | 100 | Reuses /api/branches/ and /api/invites/ (M1-03, M2-07) | company-admin.tsx – quick-create shortcuts in dashboard view | Y | N | High | Read company-admin.tsx – branch/user create modals accessible from dashboard tab | None | —
M3-07 | Company-wide search | M3 – Company Admin Dashboard & Monitoring | Should | Medium | Partially Working | 50 | queuing/views.py:TicketViewSet has search by phone (customer_phone_index blind index); no dedicated global search endpoint | super-admin.tsx – global search bar (line 35) searches local state only | N | N | High | Searched all backend for GlobalSearch¦global_search¦search_customers – no dedicated endpoint; super-admin.tsx search filters state.companies array locally | No server-side cross-entity search; frontend search only covers local state | Implement GET /api/search/?q= endpoint across Ticket/Appointment/Customer
M4-01 | Queue method activation per branch | M4 – Branch Operator Configuration Panel | Must | Medium | Fully Working | 100 | queuing/models.py:QueueMethod (method, is_enabled, config per branch); QueueMethodViewSet; /api/queue-methods/ | branch-desks-services.tsx – method toggle switches | Y | Y – test_phase2.py passes | High | Ran pytest tests/test_phase2.py – relevant tests pass; read QueueMethod model | None | —
M4-02 | Desk/counter setup | M4 – Branch Operator Configuration Panel | Must | Medium | Fully Working | 100 | queuing/views.py:DeskViewSet, DeskServiceViewSet; /api/desks/, /api/desk-services/ | branch-desks-services.tsx (156 KB) – full desk CRUD | Y | Y – test_phase2.py passes | High | Ran pytest test_phase2.py – desk tests pass; tested with test_rbac.py (some RBAC tests fail – see M8-03) | test_rbac.py::test_desk_service_permissions_by_role FAILS | Fix RBAC permission check on desk-service endpoint
M4-03 | Service catalogue | M4 – Branch Operator Configuration Panel | Must | Low | Fully Working | 100 | queuing/views.py:ServiceViewSet; /api/services/; Service.est_service_minutes, is_active fields | branch-desks-services.tsx – service catalog tab | Y | Y – test_phase2.py passes | High | Ran pytest test_phase2.py | None | —
M4-04 | QR code generation & branding | M4 – Branch Operator Configuration Panel | Must | Low | Partially Working | 50 | queuing/views.py:QrCodeGenerateView; /api/branches/{id}/generate-qr/; generates SVG via qrcode lib; qrcodes/ folder has 9 SVGs | branch-desks-services.tsx – QR code preview; test_rbac.py::test_qr_code_permissions_by_role FAILS (assert 200==403) | Y | N – test_rbac.py::test_qr_code_permissions_by_role FAILED | High | Ran pytest tests/test_rbac.py::test_qr_code_permissions_by_role – FAILED; QR returns 200 for a role that should get 403 | RBAC gate on QrCodeGenerateView missing – wrong role can generate QR (test_rbac.py FAILS) | Add IsBranchAdmin permission to QrCodeGenerateView; fix test_rbac.py::test_qr_code_permissions_by_role
M4-05 | Token numbering rules | M4 – Branch Operator Configuration Panel | Must | Medium | Fully Working | 100 | queuing/models.py:TokenSequence (atomic daily counter); QueueMethod.config.numbering_style (sequential/prefix); reset at midnight implicit via date field | branch-desks-services.tsx – token rule config section | Y | Y – test_phase2.py passes | High | Read TokenSequence.get_next_sequence_number() – select_for_update() atomic; tested in test_phase2.py | None | —
M4-06 | Display screen layout config | M4 – Branch Operator Configuration Panel | Should | Medium | Scaffolded | 25 | display/models.py:DisplayDevice (model only); display/views.py is empty (4 lines, no implementation) | N/A – no display config UI in branch-console.tsx or branch-desks-services.tsx found | N | N | High | Read display/views.py – only 'from django.shortcuts import render # Create your views here.'; DisplayDevice model exists with 0 routes | display app has model but zero views/routes; no frontend UI for pairing code | Implement DisplayDevice CRUD views, register in urls.py, add frontend UI
M4-07 | Printer configuration (KOT) | M4 – Branch Operator Configuration Panel | Should | Medium | Fully Working | 100 | kot/views.py:PrinterViewSet, PrinterHeartbeatView, PrinterJobsView; /api/kot/printers/ | branch-desks-services.tsx – printer config tab | Y | Y – test_phase3.py passes | High | Ran pytest tests/test_phase3.py – passes | Printer auth uses PrinterToken scheme (not JWT); physical ESC/POS bridge not in scope | —
M4-08 | Remote appointment settings (Method 4) | M4 – Branch Operator Configuration Panel | Must | Medium | Fully Working | 100 | appointments/views.py:AppointmentSlotViewSet, BulkSlotCreateView, TimeSlotViewSet; /api/slots/, /api/time-slots/ | branch-console.tsx – appointments configuration tab | Y | Y – test_phase4.py passes | High | Ran pytest tests/test_phase4.py – passes | None | —
M4-09 | Branch operating hours & holidays | M4 – Branch Operator Configuration Panel | Must | Low | Fully Working | 100 | branches/models.py:Branch.operating_hours JSONField; BranchViewSet allows partial_update | branch-console.tsx – operating hours editor | Y | N | High | Read branches/models.py – operating_hours is JSONField (flexible schema); BranchViewSet confirms it's patchable | Holiday calendar is a free JSONField with no schema enforcement | Validate operating_hours JSON structure in BranchSerializer
M4-10 | Staff shift/roster (new) | M4 – Branch Operator Configuration Panel | Could | Medium | Scaffolded | 25 | queuing/models.py:DeskStaffAssignment (shift_start, shift_end); DeskStaffAssignmentViewSet; /api/desk-staff-assignments/ | branch-desks-services.tsx – partial shift assignment UI (assigns staff to desk, not full roster) | N | N | High | Read DeskStaffAssignment model – has shift_start/end fields but no roster view or calendar UI; routing logic does not check shift_start/end before assigning tickets | Queue routing (queue_routing.py) doesn't check DeskStaffAssignment is_active/shift_start/end before routing – shift data exists but isn't used for routing | Update assign_predicted_desk_for_ticket() to filter desks to on-duty staff only
M5-01 | Method 1: QR landing + registration | M5 – Queuing Solution Methods | Must | Medium | Fully Working | 100 | queuing/views.py:PublicJoinQueueView; POST /api/public/join/; throttled (PublicSubmitThrottle) | src/routes/q.$branchId.tsx (18 KB) – scan → name/contact/message → token issued | Y | Y – test_phase2.py::test_public_join_queue passes | High | Ran pytest test_phase2.py – passes; read q.$branchId.tsx flow | None | —
M5-02 | Method 1: Operator serve console | M5 – Queuing Solution Methods | Must | Medium | Fully Working | 100 | queuing/views.py:TicketViewSet (call_next, action); /api/tickets/call-next/, /api/tickets/{id}/action/ | src/routes/app.tsx desk console tab; branch-console.tsx – ordered queue list, call/serve/close/notes | Y | Y – test_phase2.py passes | High | Ran pytest test_phase2.py; read TicketViewSet actions | None | —
M5-03 | Method 2: Service selection & desk routing | M5 – Queuing Solution Methods | Must | Medium | Fully Working | 100 | queuing/services/queue_routing.py:assign_predicted_desk_for_ticket(); Ticket.save() invokes it; DeskService links desks to services | q.$branchId.tsx – service selector before join | Y | Y – test_phase2.py passes; test_scenario57.py::test_negative_qualification_removal FAILED | High | Ran pytest – routing tests pass; test_scenario57.py failure is edge-case (negative seat removal), main routing works | test_scenario57.py::test_negative_qualification_removal FAILED – edge case in re-evaluation logic | Fix reevaluate_predictions_for_desk for negative qualification edge case
M5-04 | Method 3: Live 'Now Serving' display board | M5 – Queuing Solution Methods | Must | High | Fully Working | 100 | queuing/views.py:PublicDisplayView (grep confirmed class exists in views.py); /api/public/display/{branch_id}/ → 200 confirmed; WS group=branch_{id}_public | src/routes/display.$branchId.tsx (594 lines) – full-screen board, WS connection at line 327, 20s poll fallback | Y | Y – hit /api/public/display/1/ via Invoke-WebRequest → 200 with real branch/desk/ticket data | High | Invoked GET http://127.0.0.1:8000/api/public/display/1/ – 200 with keys [branch, company, desks, services, tickets]; read display.$branchId.tsx WS connect logic | display/views.py is an empty app stub – PublicDisplayView lives in queuing/views.py (correct); no separate display app routes needed | —
M5-05 | Method 4: Public booking portal | M5 – Queuing Solution Methods | Must | High | Fully Working | 100 | appointments/views.py:PublicOnlineBookingCreateView, PublicCompanyResolveView; /api/public/bookings/, /api/public/company/{slug}/ | src/routes/$companySlug.tsx (30 KB) – full booking flow; src/routes/book.tsx (12 KB) | Y | Y – test_phase4.py passes | High | Ran pytest test_phase4.py – passes | CAPTCHA is MOCK_CAPTCHA_TOKEN in $companySlug.tsx:187 | Integrate real CAPTCHA before production
M5-06 | Method 4: OTP verification | M5 – Queuing Solution Methods | Must | Medium | Partially Working | 50 | appointments/views.py:OtpSendView, OtpVerifyView; /api/public/appointments/otp/send¦verify/ | $companySlug.tsx – OTP step; src/components/quesole/otp.tsx | N | Y – test_phase4.py passes (uses console backend) | High | Ran pytest test_phase4.py – OTP tests pass; read .env – SMS_BACKEND=console (real SMS not sent) | SMS_BACKEND=console – real SMS not delivered; no MSG91/Twilio credentials in .env | Configure MSG91_AUTH_KEY or TWILIO credentials
M5-07 | Method 4: Appointment management | M5 – Queuing Solution Methods | Should | Medium | Fully Working | 100 | appointments/views.py:AppointmentManageView, AppointmentRescheduleView, AppointmentCancelView; /api/public/appointments/manage/{code}/reschedule¦cancel/ | $companySlug.tsx – manage section with reschedule/cancel | Y | Y – test_phase4.py passes | High | Ran pytest test_phase4.py – appointment management tests pass | None | —
M5-08 | Unified queue view (walk-in + appointment) | M5 – Queuing Solution Methods | Must | Medium | Partially Working | 50 | queuing/views.py:TicketViewSet returns all tickets (walk-in + appointment source); appointment tickets created via appointments/signals.py | branch-console.tsx – single queue list; test_phase4.py::test_prioritized_unified_queue FAILED (assert 16==14) | N | N – test_phase4.py::test_prioritized_unified_queue FAILED | High | Ran pytest – test_prioritized_unified_queue FAILED (position count mismatch 16 vs 14) – unified ordering broken | test_phase4.py::test_prioritized_unified_queue FAILED – appointment+walk-in ordering logic bug | Fix unified queue sort/prioritization in TicketViewSet
M5-09 | Customer token status tracking page | M5 – Queuing Solution Methods | Must | Medium | Fully Working | 100 | queuing/views.py:PublicTicketDetailView, PublicTrackingView; /api/public/ticket/{id}/, /api/public/tracking/{code}/ | src/routes/t.$ticketId.tsx (7 KB) – position + ETA display | Y | N – no test for public tracking endpoint | High | Read t.$ticketId.tsx – calls /api/public/ticket/{id}/ which is registered and implemented; PublicTicketDetailView confirmed in queuing/views.py | None | Add test_public_tracking.py
M5-10 | Queue transfer / re-route | M5 – Queuing Solution Methods | Should | Low | Fully Working | 100 | queuing/views.py:TicketViewSet action() handles transfer/redirect; Ticket.desk can be reassigned | branch-console.tsx – transfer button in ticket action menu | Y | N | High | Read TicketViewSet action() – transfer case updates desk_id and re-broadcasts; UI confirmed in branch-console.tsx | None | Add transfer test
M6-01 | Fully responsive staff/admin console | M6 – Responsive Web Access | Must | Medium | Fully Working | 100 | N/A | All console components use Tailwind responsive classes (sm:/lg:); shell.tsx has mobile-first sidebar | Y | N | High | Read shell.tsx – sidebar collapses on mobile; branch-console/company-admin use responsive grid | None | —
M6-02 | Browser push notifications | M6 – Responsive Web Access | Should | Medium | Not Started | 0 | N/A – searched all .py for FCM¦firebase¦vapid¦push_notification – no results | N/A – searched all .tsx for PushManager¦ServiceWorker¦Notification.requestPermission – no results | N | N | High | grep backend for FCM¦firebase¦vapid; grep frontend for PushManager¦ServiceWorker – zero hits | Feature entirely absent | Implement Web Push (VAPID key + service worker) or Firebase FCM integration
M6-03 | Installable Progressive Web App (PWA) | M6 – Responsive Web Access | Could | Medium | Not Started | 0 | N/A | public/ has no manifest.json or sw.js; vite.config.ts has no vite-plugin-pwa | N | N | High | Listed public/ directory – no manifest.json or service worker; checked vite.config.ts – no PWA plugin | No manifest, no service worker, no install prompt | Add vite-plugin-pwa; create public/manifest.json
M6-04 | Offline-tolerant queue view (PWA) | M6 – Responsive Web Access | Could | High | Not Started | 0 | N/A | N/A – depends on M6-03 which is Not Started | N | N | High | M6-03 is Not Started; offline caching not possible without service worker | Depends on M6-03 (PWA) which is not started | Implement M6-03 first
M7-01 | Kiosk touch-screen service selection | M7 – KOT Printing | Must | Medium | Fully Working | 100 | kot/views.py:KioskJoinView; POST /api/kiosk/join/ | src/routes/kiosk.$branchId.tsx (52 KB) – touch UI with service selector | Y | Y – test_phase3.py passes | High | Ran pytest test_phase3.py – kiosk join tests pass | None | —
M7-02 | Physical token print | M7 – KOT Printing | Must | Medium | Partially Working | 50 | kot/models.py:KotPrintJob (queued→printed); PrinterJobsView/PrinterJobCompleteView for device polling | kiosk.$branchId.tsx – triggers print job on token issue | N | Y – test_phase3.py passes for print job creation; physical printer not testable | High | Ran pytest test_phase3.py – print job creation passes; physical ESC/POS bridge is external hardware – cannot test in this environment | Physical ESC/POS printer bridge is external hardware (cannot verify in dev) | Test with actual ESC/POS printer or USB bridge agent
M7-03 | Unified digital sync | M7 – KOT Printing | Must | Medium | Fully Working | 100 | kot/views.py:KioskJoinView calls broadcast_queue_update() → WebSocket push to operators; Ticket created with source_method=KOT_PRINT | branch-console.tsx receives WS update showing kiosk ticket in queue | Y | Y – test_phase3.py passes | High | Read KioskJoinView:70 – broadcast_queue_update(branch.id, ticket) called after Ticket.objects.create; test_phase3.py passes | None | —
M7-04 | Printer health monitoring | M7 – KOT Printing | Should | Medium | Fully Working | 100 | kot/views.py:PrinterHeartbeatView; POST /api/kot/heartbeat/; triggers dispatch_notification() on offline status | branch-desks-services.tsx – printer status indicators | Y | Y – test_phase3.py covers heartbeat | High | Ran pytest test_phase3.py – printer heartbeat tests pass; read PrinterHeartbeatView:99 – dispatches alert on offline | Kiosk staff-override PIN: searched backend for pin¦kiosk_pass¦override_pin – kiosk_password_hash exists in Branch model; no separate PIN endpoint; kiosk.$branchId.tsx:679 PIN input exists but no API call found | Wire kiosk.$branchId.tsx PIN field to POST /api/kot/staff-override/ endpoint (needs creating)
M8-01 | Staff/admin login (JWT) | M8 – Auth, RBAC & Multi-Tenancy | Must | Medium | Fully Working | 100 | accounts/views.py:CustomTokenObtainPairView, LogoutView, TokenRefreshView; /api/auth/login¦logout¦refresh/; simplejwt blacklist | src/routes/login.tsx (18 KB); store.tsx:signIn() | Y | Y – test_auth.py all 5 pass | High | Ran pytest tests/test_auth.py – all 5 tests pass | JWT key < 32 bytes (InsecureKeyLengthWarning in test output) – not blocking but should be fixed | Set SECRET_KEY ≥ 32 bytes in .env
M8-02 | Password reset / forgot password | M8 – Auth, RBAC & Multi-Tenancy | Must | Low | Scaffolded | 25 | N/A – confirmed no password reset endpoint in queuing_solutions/urls.py or accounts/views.py; searched all urls.py files | src/routes/forgot-password.tsx (7 KB) – UI exists (email input + submit) | N | N | High | grep queuing_solutions/urls.py for 'password' – zero results; grep accounts/views.py for 'reset¦forgot' – zero results; accounts/ has no urls.py; forgot-password.tsx has UI but no API call confirmed | Zero backend implementation – no reset token generation, no email dispatch, no confirm endpoint | Implement POST /api/auth/password-reset/ + /api/auth/password-reset/confirm/ in accounts/views.py
M8-03 | Role-Based Access Control (RBAC) | M8 – Auth, RBAC & Multi-Tenancy | Must | High | Partially Working | 50 | core/permissions.py:IsSuperAdmin, IsCompanyAdmin, IsBranchAdmin, IsDeskStaff, IsBranchAdminOnly; applied consistently | app.tsx role-gated navigation; store.tsx role checks | N | N – test_rbac.py: 4 FAILED (test_desk_service_permissions_by_role, test_qr_code_permissions_by_role, test_kot_printer_permissions_by_role, test_company_users_permissions_by_role) | High | Ran pytest tests/test_rbac.py – 4 tests FAIL: QR endpoint returns 200 for unauthorized role; desk-service returns 400 instead of 403; KOT printer returns 400 instead of 403; company users returns 200 instead of 403 | 4 RBAC tests fail – missing permission guards on QR, desk-service, KOT printer, and company users endpoints | Add correct IsCompanyAdminOnly/IsBranchAdmin guards to failing endpoints; fix test_rbac.py
M8-04 | Tenant data isolation | M8 – Auth, RBAC & Multi-Tenancy | Must | High | Fully Working | 100 | core/managers.py:TenantManager applied to all models; filters by company automatically; test_tenant_isolation.py | store.tsx company-scoped data fetching | Y | Y – test_tenant_isolation.py (3 pass) | High | Ran pytest tests/test_tenant_isolation.py – all 3 pass | None | —
M8-05 | Two-Factor Authentication (2FA) | M8 – Auth, RBAC & Multi-Tenancy | Should | Medium | Not Started | 0 | N/A – searched for django_otp¦two_factor¦totp – no project code found (only venv/library files) | N/A | N | N | High | grep backend project files (excluding venv/) for totp¦django_otp¦2fa – zero project-code hits | Feature entirely absent | Implement with django-otp or django-allauth 2FA
M8-06 | Session/device management | M8 – Auth, RBAC & Multi-Tenancy | Could | Low | Scaffolded | 25 | simplejwt TokenBlacklist on logout; no active session listing or device revocation endpoint | N/A | N | N | High | LogoutView blacklists refresh token (confirmed in test_auth.py); no /api/auth/sessions/ endpoint to list or revoke individual devices | Single-device logout only; no multi-device session management | Implement outstanding token listing + selective revocation
M9-01 | Trigger rule engine | M9 – Alerts & Notifications Engine | Must | High | Fully Working | 100 | notifications/models.py:AlertRule (trigger_type, threshold, is_active); notifications/tasks.py – 8 check_* tasks that evaluate AlertRule objects | company-admin.tsx – alert rules tab | Y | Y – invoked check_long_wait_times() directly; Notification count confirmed ≥ 0; notifications/tests.py empty but test_phase7.py covers partial | High | Called check_long_wait_times() in Django shell – executed without error; AlertRule model confirmed via migrations | Celery must be running for production; empty notifications/tests.py | Write tests for each of the 8 trigger types
M9-02 | Multi-channel delivery | M9 – Alerts & Notifications Engine | Must | High | Scaffolded | 25 | notifications/tasks.py:dispatch_notification() routes to channel (in_app/sms/email/whatsapp); accounts/services/ dir exists; SMS_BACKEND=console | N/A | N | N | High | Read dispatch_notification() – channel routing code exists; SMS_BACKEND=console in settings means no real SMS/email; no MSG91/Twilio/SendGrid credentials in .env | Only in_app channel works; SMS/email/WhatsApp channels go to console stdout | Configure SMS and email gateway credentials in .env
M9-03 | Notification preferences | M9 – Alerts & Notifications Engine | Should | Low | Not Started | 0 | N/A – no UserNotificationPreference model or endpoint found | N/A – no notification preferences UI found in console components | N | N | High | Searched all models.py for NotificationPreference¦UserPreference – zero hits | Feature entirely absent | Implement UserNotificationPreference model + /api/notification-preferences/ endpoint
M9-04 | Scheduled report delivery | M9 – Alerts & Notifications Engine | Should | Medium | Not Started | 0 | N/A – analytics/tasks.py has nightly ReportSnapshot aggregation, but no scheduled email delivery of reports | N/A | N | N | High | Read analytics/tasks.py and notifications/tasks.py – no send_scheduled_report or email_report task found | Feature entirely absent | Implement Celery task to email CSV exports on schedule
M9-05 | In-app notification center | M9 – Alerts & Notifications Engine | Must | Low | Fully Working | 100 | notifications/models.py:Notification; /api/notifications/ (list, mark read) | shell.tsx – notification bell with unread badge; company-admin.tsx alert feed | Y | N | High | Read NotificationViewSet – list/create/update (mark read) confirmed; shell.tsx bell component confirmed; 8 notifications in DB confirmed | None | —
M10-01 | Operational KPIs | M10 – Reporting & Analytics | Must | Medium | Fully Working | 100 | analytics/views.py:ReportTrendsView returns total_tickets, served_count, avg_wait, avg_handle per day | company-admin.tsx – operational KPI cards | Y | Y – test_phase5.py passes | High | Ran pytest test_phase5.py – passes; confirmed ReportTrendsView endpoint returns correct keys | None | —
M10-02 | Peak-hour heatmap | M10 – Reporting & Analytics | Should | Medium | Fully Working | 100 | analytics/views.py:ReportTrendsView returns peak_hours dict (hour→count) | company-admin.tsx – peak hour heatmap chart | Y | N | High | Read ReportTrendsView:63 – peak_hours aggregated from snapshot metrics; frontend chart confirmed in company-admin.tsx | Requires Celery nightly task to populate ReportSnapshot | Run analytics aggregation Celery task to seed data
M10-03 | Staff/operator performance | M10 – Reporting & Analytics | Should | Medium | Fully Working | 100 | analytics/views.py:ReportTrendsView returns staff_summary (operator_id→served_count, avg_handle) | company-admin.tsx – staff performance tab | Y | N | High | Read ReportTrendsView:66 – staff_summary built from snapshot metrics | None | —
M10-04 | Branch comparison report | M10 – Reporting & Analytics | Should | Medium | Fully Working | 100 | analytics/views.py:ReportTrendsView returns branch_comp dict | company-admin.tsx – branch comparison section | Y | N | High | Read ReportTrendsView:79 – branch_comp dict populated | None | —
M10-05 | Customer feedback/rating (future-pull-forward) | M10 – Reporting & Analytics | Could | Medium | Scaffolded | 25 | feedback/models.py:Feedback (rating, comment, ticket FK, appointment FK); no views.py, no urls.py, no router registration | N/A – no feedback collection UI found in any route or component | N | N | High | Listed feedback/ directory – only apps.py, models.py, migrations/ (no views, no urls, no admin); frontend grep for feedback¦rating – no UI component found | Model only; no API surface and no UI | Implement views.py, urls.py, and post-service feedback form
M10-06 | API/data export for BI tools | M10 – Reporting & Analytics | Could | Medium | Partially Working | 50 | analytics/views.py:ReportExportView returns CSV via pandas; /api/reports/export/ | company-admin.tsx – export CSV button | Y | N | High | Read ReportExportView – uses pandas to_csv(); endpoint registered in urls.py | Only CSV; no JSON:API or BI-connector format; no scheduled push to BI tools | Add JSON export option; document BI integration pattern
M11-01 | Audit logging | M11 – Cross-Cutting Platform Concerns | Must | Medium | Fully Working | 100 | audit/models.py:AuditLog; audit/utils.py:log_audit() called in accounts, companies, billing, queuing views; /api/audit-logs/ | super-admin.tsx – audit log tab | Y | N – audit/tests.py is 60-byte stub | High | Read log_audit() – called in ~8 different views; AuditLogViewSet confirmed in urls.py | No audit tests | Write test_audit.py
M11-02 | Multi-language / i18n | M11 – Cross-Cutting Platform Concerns | Should | Medium | Not Started | 0 | N/A | N/A – searched all .tsx files for i18n¦useTranslation¦t( – zero hits; no i18n library in package.json | N | N | High | grep src/ for i18n¦useTranslation – zero hits; checked package.json – no i18next or react-intl | Feature entirely absent | Add i18next or react-intl; externalize all UI strings
M11-03 | Data privacy / consent | M11 – Cross-Cutting Platform Concerns | Must | Low | Fully Working | 100 | queuing/models.py:Ticket.customer_consented_at; EncryptedCharField on customer_phone; blind_index for search; core/tasks.py:purge_expired_customer_pii() | q.$branchId.tsx – consent checkbox before join; $companySlug.tsx – consent checkbox on booking | Y | Y – test_phase7.py covers PII purge | High | Ran pytest test_phase7.py – PII purge test passes; read consent_at field in model | None | —
M11-04 | Rate limiting & abuse protection | M11 – Cross-Cutting Platform Concerns | Must | Medium | Partially Working | 50 | core/throttles.py:PublicBurstThrottle, PublicSubmitThrottle, CompanySignupThrottle; core/honeypot.py; applied to PublicJoinQueueView, CompanyRegistrationView | N/A | N | N – test_phase2.py::test_anon_rate_limiting FAILED (assert 400==201) | High | Ran pytest test_phase2.py::test_anon_rate_limiting – FAILED; throttle test asserts wrong status code (got 201 instead of 400 after burst) | test_anon_rate_limiting FAILS – throttle may be too permissive in test environment (ANON_THROTTLE_RATES not set for test) | Set TEST_THROTTLE_RATES or configure throttle override in test settings
M11-05 | Payment gateway integration | M11 – Cross-Cutting Platform Concerns | Must | High | Partially Working | 50 | billing/stripe_helper.py; billing/views.py:StripeWebhookView, CheckoutSessionView; StripeSimulatorView as sandbox | signup.tsx – payment step | N | N | High | Read .env – STRIPE_SECRET_KEY not set; StripeSimulatorView (sandbox) is functional but not real Stripe | STRIPE_SECRET_KEY absent from .env | Add test Stripe key; run checkout against Stripe sandbox
M11-06 | SMS/OTP gateway integration | M11 – Cross-Cutting Platform Concerns | Must | Medium | Scaffolded | 25 | accounts/services/ dir exists; notifications/tasks.py:dispatch_notification() has SMS routing; OtpSendView uses SMS_BACKEND | N/A | N | N | High | Read .env and settings.py – SMS_BACKEND=console; no MSG91_AUTH_KEY or TWILIO_ACCOUNT_SID present | SMS_BACKEND=console – no real SMS gateway configured | Configure MSG91_AUTH_KEY or TWILIO credentials; set SMS_BACKEND=msg91
M11-07 | File/export storage | M11 – Cross-Cutting Platform Concerns | Must | Low | Partially Working | 50 | django.core.files.storage:default_storage used for QR SVG files (in queuing/views.py); qrcodes/ directory has 9 SVG files | N/A | N | N | High | Read settings.py – DEFAULT_FILE_STORAGE is django local storage (no S3); qrcodes/ dir has 9 SVGs stored locally; production would need S3/GCS | Local file storage only – not suitable for multi-server production deployment | Configure django-storages with S3 backend
M11-08 | Health checks & monitoring | M11 – Cross-Cutting Platform Concerns | Must | Low | Partially Working | 50 | core/views.py:healthz at /healthz; /metrics returns Prometheus data (200 confirmed) | N/A | N | N | High | Hit /metrics via Invoke-WebRequest – 200 with prometheus_gc data; hit /healthz – returns 503 (Service Unavailable) – DB check in healthz fails in current dev setup | /healthz returns 503 – DB connectivity check in healthz view fails; /metrics works | Debug healthz: check why DB check returns unavailable (may be DB not initialized in test)
M11-09 | API documentation | M11 – Cross-Cutting Platform Concerns | Should | Low | Fully Working | 100 | drf_spectacular; /api/schema/, /api/docs/ (Swagger), /api/redoc/ | N/A | Y | N | High | URL confirmed in urls.py:63-65; drf_spectacular in INSTALLED_APPS in settings.py | None | —
M11-10 | Backup & disaster recovery | M11 – Cross-Cutting Platform Concerns | Must | Medium | Partially Working | 50 | core/backup.py:run_mysql_backup(); core/tasks.py:purge_expired_customer_pii(); CELERY_BEAT_SCHEDULE entries | N/A | N | Y – test_phase7.py covers PII purge; backup file creation not tested | High | Read core/backup.py – calls mysqldump subprocess; Celery beat schedules confirmed in settings.py; purge_expired_customer_pii passes in test_phase7.py; mysqldump must be on PATH | Celery beat must be running; mysqldump must be on PATH (XAMPP installs it in MySQL bin); no DR runbook | Confirm mysqldump in PATH; start Celery beat; create DR runbook

## Untracked - Extra Code
Path / Location | Description | Risk
completed_modules.xlsx (root + public/) | Separate UI polish tracker (MOD-01…MOD-10) for frontend visual improvements; not in main breakdown sheet | Low
src/components/site/scroll-controlled-background.tsx | Scroll-linked background video – frontend-only visual enhancement; not in any M0-M11 module | Low
backend/tests/locustfile.py | Locust load-test script (~200 lines); not in breakdown spec but useful for NFR testing | Low
backend/tests/test_scenario57.py | Specific scenario test (named 'scenario57'); 1 test FAILS – negative qualification removal edge case | Medium – failing test
backend/tests/test_phase6.py | Phase 6 test file (6 KB); covers security/compliance tests not in M0-M11 breakdown | Low
backend/tests/test_phase7.py | Phase 7 test file (36 KB – largest); covers data retention, backup, WebSocket Redis – beyond main spec | Low
billing/stripe_helper.py | Stripe wrapper module (3 KB); not listed as standalone module in breakdown | Low
core/honeypot.py | Bot honeypot field validator – security extra beyond spec items | Low
core/throttles.py | Custom DRF throttle classes – referenced in spec (M11-04) but implemented as standalone module | Low
core/crypto.py | Blind-index + tracking-code generator – PII encryption support beyond explicit spec | Low
backend/subscriptions/ | Empty subscriptions/ app (only services/ subdir); functionality consolidated into billing/ | Low – no routes
qrcodes/ (root) | Static directory of pre-generated SVG QR codes; not a Django app | Low
src/routes/book.tsx | Standalone 12 KB route; partial overlap with $companySlug.tsx booking flow – may be dead code or alternate flow | Medium – may be dead code
src/lib/quesole/store.tsx:1601 | Dashboard delta percentages (vs. yesterday) computed client-side in store.tsx – not from a backend API aggregate | Low – cosmetic
src/components/site/sections.tsx | Large marketing page sections (visual only) – fully working but no mapping to spec module | Low
backend/display/ | display/ Django app exists with DisplayDevice model but zero views/routes – dead app stub beyond display board | High – empty app causes confusion